## Sheet1
QA | [9 empty] | DEVELOPER
Bug ID | Defect Description | Steps to Reproduce | Expected Result | Actual Result | Priority | Device name or Browser name | Severity | Screen Shot | Submitted By | Resolution Types | Status | Fixed By | Fixed DATE
B01 | Empty Video link uploaded | 1.Log into livecx.com. 2. Go to Map Experiences. 2. See the Map post. 3. Click on the post. 4. Click on the step. 5. Tap on the video. | Without a link, the video should not be added | Without a link, video is adding | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 | High | Empty video | Md. Bashir Ahmed
B02 | Cancel button not working | 1. Log in to livecx.com. 2 .Go to Map Experiences. 3. See the Map post. 4. Click on the post. 5. Click on the step. 6. Tap on comments. 7. Write something then click on Cancel | Cancel Button Should work properly. | The cancel button is not working | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 | High | Cancel | Md. Bashir Ahmed
B03 | Unable to post comment | 1. Log in to livecx.com . 2. Go to Map Experiences. 3. See the Map post. 4. Click on the post. 5. Click on the step. 5. Tap on comments and write something. 6. Click on the post button. | Comments should be posted. | User can't able to post comment | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 | High | Comments | Md. Bashir Ahmed
B04 | Empty Message is sending | 1. Log in to livecx.com. 2. See right bottom of the window. 3. Click on the "^" icon at the inline of the user name. 4. Click on a connected user. Type nothing. 5. Click on send icon button. | User should not able to send empty message | The message is sent with blank data. | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 | High | Empty Message | Bashir Ahmed
B05 | Can't be Published in Map Journeys without a photo. | 1.Log in to livecx.com . 2. Go to CX Brainstorm. 3. Click on Telecom. 4. Click on any of the cards like "I Am Searching For A Deal" 5. Click on Map Journeys then write something and published it. | Should give proper error message | The invalid error message is showing | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 93.0.4577.63 (Official Build) (64-bit)) Browser: Micro Edge (Version 93.0.961.47 (Official build) (64-bit)) Resolution: 1920*1080 | High | error message | Bashir Ahmed
B06 | Messaging Input text field change | 1. Log in to livecx.com . 2. See the right bottom of the window. 3. Click on the "^" icon at the inline of the user name. 4. Click on a connected user. See the messaging input text field placeholder. | Input field should amend the text from “Write message” to “Write a message…” | "Write message" is given as placeholder on input filed | Low | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 | Low | Change Text | Bashir Ahmed
B07 | Remove "Chat icon" next to the text “Write message” | 1. Log in to livecx.com. 2. See the right bottom of the window. 3. Click on the "^" icon at the inline of the user name. 4. Click on a connected user. See the messaging input text field chat icon | Chat icon should remove next to the text "Write message" | The icon is visible before chat input field placeholder | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 | Low | Remove chat icon | Bashir Ahmed
B08 | Emoji icon added in the below-chatting panel | 1. Log in to livecx.com 2. See the right-bottom of the window. 3. Click on the "^" icon at the inline of the user name. 4. Click on a connected user. See under the messaging panel. | In the panel below – in addition to the attachment icon show the Emoji icon. | Emoji icon is missing | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 | Low | Emoji Icon add | Bashir Ahmed
B09 | The date/time of chatting is missing. | 1. Log in to livecx.com. 2. See the right bottom of the window. 3. Click on the "^" icon at the inline of the user name. 4. Then see the connection user message list. | The date/time of the chatting message should be shown. | The date/time of the chat message is not showing | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 | Low | Display message | Bashir Ahmed
B10 | "Separate the chat messages with a light grey line" is missing | 1. Log in to livecx.com. 2. See the right bottom of the window. 3. Click on the "^" icon at the inline of the user name. Then see the connection user message list. | Separate lines for chat messages should be added. | Separate lines for chat messages are not added | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 | Low | Separate Messages line | Bashir Ahmed
B11 | Attachment viewing | 1. Log in to livecx.com . 2. See right bottom of the window. 3. Click on the "^" icon at the inline of the user name. Then see the connection user message list. 4. Click on a connection user member. click on the attachment photo. | Users can able to open the attachment and can download and view it on full screen as per client requirements. | The attachment does not open | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 | High | Attachments | Bashir Ahmed
B12 | Active status visibility | 1. Log in to livecx.com . 2. See the right bottom of the window. 3.Click on the "^" icon at the inline of the user name. 4. Then see the connection user message list. 5. Click on connection user member. | Users can able to open the attachment and can download and view it in full screen as per client requirements. | Connection member's Status is always showing online after he is logged out from his account | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 | High | Connection members status | Bashir Ahmed
B13 | Pin option is not working | 1. Log in to livecx.com . 2. Click on CX Brainstorm. 3. Click on Telecom. 4. Click on Map journeys. 5. Click on a Map. Then click on the 3 dot button. 6. See the Pin option. | Pin option should work properly. | Pin option is not working | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 | High | Pin | Bashir Ahmed
B14 | Archive option is not working. | 1. Log in to livecx.com. 2. Click on CX Brainstorm. 3. Click on Telecom. 4. Click on Map journeys. 5. Click on a Map. Then click on the three-dot button. 6. See the Archive option. | Archive option should work properly. | The archive option is not working | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 | High | Archive | Bashir Ahmed
B15 | Drag and Drop is working but Error Message is shown. | Log in to livecx.com . Click on CX Brainstorm. Click on Telecom. Then click on Map journeys. Click on a Map named Testing journey consolidation. Try to drag & drop to change position. See the error message. | Error Message should not be shown. | Error message is showing | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 |  | Drag and Drop | Bashir Ahmed
B16 | Drag and Drop functionality in full screen | 1. Log in to livecx.com. 2. Click on CX Brainstorm. 3. Click on Telecom. 4. Click on Map journeys. Click on a Map named Testing journey consolidation. 5. Click on Full-Screen button. 6. Try to Drag & Drop. | Drag and Drop Should work on Full Screen. | Drag and Drop is not working in Full Screen | High | DeviceName: Dekstop, Windows 10 Browser: Chrome (Version 92.0.4515.107 (Official Build) (64-bit)) Browser: Mozilla Firefox(Version 91.0.2 (Official build) (64-bit)) Resolution: 1920*1080 | High | Drag and Drop | Bashir Ahmed